## Active Items
No. | Topic | Status | Responsible Party | Date Assigned | Date Due | Date Completed
1 | Locate ICP |  | LSC
2 | Develop/Update Objectives |  | PIC/PSC
3
4
5
6
7
LONGER TERM ITEMS
8 | Initiate Strategic Planning |  | PSC
9
10
11
12
13
14

## Completed Items
No. | Topic | Status | Responsible Party | Date Assigned | Date Due | Date Completed
1 | Site/ project with ACOE -400K | Cecilia will provide statement of work to ERBs' chiefs. Still looking for a project and waiting to hear from ACOE on availability | chiefs | 2011-05-01 |  | 2011-06-13
2 | Rad IA With Argonne/ DOD | Analytical services with Argonne and Rad orphan sources with DOD Rock Island | Cecilia/ Ostrodka | 2011-05-01 | 2011-06-30 | 2011-06-13
3 | Develop 2011 equipment list | Mike provided a second list of equipment- needs approval from ERBs Chiefs | Mitchell/Ribordy | 2010-10-01 | 2011-04-30 | 2011-06-13
4 | Enbridge hotwash(R5) | Final draft report submitted on 5-18-11 | Kimble/Bev | 2011-10-10 |  | 2011-07-01
5 | Update Notification Procedures | Mark Drafted new procedure. Awaiting review & comments from chiefs | Mark | 2011-06-13 | 2011-06-30 | 2011-07-11
6 | SEE Plan for 2012 | write-ups sent to Doug on 5-2-11 | Bev/ Steve | 2011-04-18 |  | 2011-07-12
7 | Replace CISM OSC | OSC Boseman agreed to being R5 OSC CISM Rep. (Nov11 training?) | Linda /Jason | 2011-07-26 |  | 2011-08-31
8 | Regional Response Plans | updated plans on March 30. final plans are due on August 31 (IMT Final Sam sent out 7/28) EOC Plan status? | Chiefs | 2011-03-11 | 2011-08-31 | 2011-09-02
9 | CORE NAR | HQ conducted R5 CORE NAR on Aug 23,11 . Awaiting regional score | Charlie/Gulch | 2011-02-22 |  | 2011-09-02
10 | National Honor Awards | nominations due Sept 6 | Chiefs | 2011-08-15 | 2011-08-30 | 2011-09-06
11 | Schedule ERBs Retreat | Scheduled for October 26 | Chiefs |  |  | 2011-09-06
12 | Develop ER schedule for FY12 | final schedule sent to OSCs and Chiefs | Mark/Charlie | 2011-07-11 | 2011-09-19 | completed
13 | End of the year report | submit write-ups to Michelle by Sept 12. final due on Sept 15, send report to Mindy Sept 19 | Michelle, Chiefs |  |  | 2011-09-19
14 | Hire 2 OSCs(external) | Received Certs. Need to schedule interviews | Charlie /Mark/Mike? | 2011-07-26 | 2011-10-31 | 101-11
15 | PDO guide book | OSC Faryan received original file from CRA. Need to update and finalize the book. Mike to provide a completion date on Sept 6 | Faryan/Ribordy |  | 2011-09-19 | 2011-09-21
16 | New OSCs 2012 PARS | Boilerplate PARS for OSCs by 9-26. Charlie & Mike working on new Strategic plan elements. | Durno/Charlie/mike |  | 2011-09-26 | 2011-09-26
17 | 2011 PARs and 2012 new Standards | complete 2011 PARS and establish 2012 PARS by 10-28-11 | Chiefs |  | 2011-10-28 | 2011-10-31
18 | State Readiness to respond | need a status update from IL, Wi, & MI | Brian | 2011-12-09 | FY-11 completed
19 | PARS Cascading Elements | Develops elements | Charlie/Mindy/Cecilia | 2011-10-26 |  | 2011-11-07
20 | G-8 & NATO Summits- NSSE | IMT monthly meting scheduled for second Wed. of each month | Jason | 2011-09-01 |  | 5/15-22/12
21 | SFD-COOP Exercise | Develop a 2 hrs COOP exercise to be conducted at the " all Supervisors" meeting on Nov 16,11 | Steve P &O |  | 2011-10-31 | 2011-11-09
22 | Green Initiatives | Working with HQ, & contactors on guidance & measures. | K. Halbur/ Durno | 2011-02-01 | on-going | ongoing
23 | Scott Masks & Communication equipment | Completed. | Borries/ Al Gebien/Jeff Borseth | 2011-08-15 | 2011-09-30 | 2011-11-30
24 | POLREP Metrics | Sent to OSCs | Mindy/Brian | 2011-10-26 |  | 2011-12-01
25 | 2012 OSC Readiness Plenary Sessions | Information on new hires, OSCs with 10,20, 30 or 40 years of service, retired OSCs, awards compiled. Pam Gallichio assisted. | Michelle |  | 2011-12-15 | 2011-12-15
26 | New laptop distribution list | Develop a plan for distributing the new SFD laptop computers | Mindy |  |  | 2011-12-13
27 | MaxiFlex | Decision made to allow OSCs to participate in MaxiFlex program when working in the office. OSCs will have to revert to regular schedule when in the field. OSCs must work standard hours (at a minimum) when on response or phone duty. | Section Chiefs |  |  | 2011-12-06
28 | Biennial report requirements for CERCLA response | Branch Chiefs issued memo to all OSCs. Mark added to Removal Task Checklist. | Branch Chiefs/Mark | 2011-04-25 | 2011-12-20 | 2011-12-20
29 | Oil OSCs | Branches were notified of Theresa's and Tricia's selection. Rick wants to meet with Jason/Charlie re: clear delineation between Planners and OSCs. Chiefs met with Tricia and Theresa to discuss responsibilities of detail positions. | Branch Chiefs | 2011-12-13 | 2012-01-31 | 2012-01-04
30 | OSC Task Force Rep | Need new R5 Representative to replace Steve Faryan. Three year term. Monthly calls and on face to face meeting. All agree Chicago OSC should be selected. Section Chiefs voted (Micke, Brown, Mendoza) - Ramon Mendoza selected. | Section Chiefs | 2012-01-03 | 2012-01-10 | 2012-01-17
31 | IT storage/cleanup of warehouse and offices | Warehouse and 5th floor common areas completed. 5th floor needs to be maintained until meeting with RA on January 24. | Mindy | 2011-05-01 | 2012-01-24 | 2011-12-11
32 | Readiness Training | Registration began 1/3/12. Instructions on TA processing sent to all attendees on 1/18/12. All OSCs and Removal Managers/Support Staff registered. | Section Chiefs Michelle | 2011-12-06 | 2012-02-05 | 2012-01-31
33 | Tribal Consultation Training | Training on 1/26/2012 (1000-1200) for OSCs and Section Chiefs with sites in areas of concern. OSCs may be able to attend via Web conference. Charlie will request location/conferencing info. | Charlie | 2011-11-08 | 2012-01-26 | 2012-01-26
34 | FPN Close-Out | Isalee sent in updates per deadline. Still working on reconciling our list with theirs. Cecilia routed our updated list to all Chiefs. Cincy has indicated they will not update their list until they receive updates from USCG. | Isalee/Cecilia | 2011-11-08 | 2012-01-25 | 2012-01-31
35 | Local Travel Clarifications | Mindy prepared document. Will route to Branch Chiefs for review before distribution. Information distributed to all staff. | Mindy | 2011-12-13 | 2012-01-31 | 2012-01-31
36 | ERR Measures | Section Chiefs to tell all OSCs to grant them Exclusive Rights to all epaosc websites. Section Chiefs ensured OSCs updated sites missing measures prior to January retreat. | Section Chiefs | 2011-12-20 | 2012-01-25 | 2012-01-25
37 | Level A/Fitness Policy Coordinator | Need to name Fitness Coordinator to manage new Level A/Fitness policy for OSCs. Suggested plan is to have Harold from Fitness Center available to answer questions. OSC (Paul Atkociunas) would represent EPA at meetings. Policy routed to all OSCs on 1/3/12. Voluntary program. Must be implemented exactly as outlined. | Charlie | 2012-01-03 | 2012-01-31 | 2012-01-31
38 | Green Initiatives | SFD policy is in the works that will include mandated green actions. Mandated list routed to OSCs for immediate implementation on 1/31/12. Jon to update Supervisor checklist. Chiefs to consider polling OSCs during mid years for progress. | All Section Chiefs | 2012-01-17 | 2012-01-25 | 2012-01-31
39 | Episodic Flexiplace | All Chiefs to check all employees episodic flexiplace status and encourage everyone to apply in anticipation of a work at home exercise. All employees can sign up for episodic regardless of time at EPA. Program is voluntary; however, if an employee does not sign up they will have to take leave if mandatory work at home situation arises. | All Chiefs | 2012-01-17 | 2012-02-14 | 2012-02-14
40 | Financial Disclosure Forms | All OSCs to submit completed forms to Branch Chiefs. All Section Chiefs to remind them. All forms due to Rick Karl before 2/15/12. | All Chiefs | 2012-01-09 | 2012-02-03 | 2012-02-15
41 | National Notable Achievement Awards | Dowagiac Site submitted for Enforcement Team of the Year. Mitchell submitted for OSC of the Year. Lippert submitted for Community Involvement. Rewrites recommended and completed. | All Chiefs | 2012-01-31 | 2012-02-15 | 2012-02-22
42 | Airline Mile Planning | Need list of all anticipated airline travel by person. Information needed includes name of person, month of travel, city travelling to, and reason for travel. List due to Division on 2/22/12. | All Chiefs | 2012-02-14 | 2012-02-21 | 2012-02-22
43 | RRT Annual Report | Sheila/Barbi/Jon to finalize draft. Draft will be forwarded to USCG for review by 2/17/12. Any USCG comments received will be considered. Final product due 2/24/12. | Jon | 2012-01-17 | 2012-02-24 | 2012-02-22
44 | New OSCs on FY 12 Response Schedule | Four new OSCs (Nightingale, Hassan, Sewell, Maguire) assigned specific weeks (both primary for their office and regional backup) for the remainder of FY12. | Charlie/Mark/Jon | 2012-01-17 | 2012-02-21 | 2012-02-22
45 | Contingency Plan Review for IG Audit | All Sub-Area Plans and RCP need to be reviewed for completeness and accuracy. IG Audit completed 1/23-24/12. Jon forwarded follow-up documentation to IG. IG hosted call with all Regions on 2/22/12. No action items for R5. | Jon/Wendy | 2011-12-06 | 2012-02-29 | 2012-02-29
46 | FPN Close-out List | New list received - Isalee has routed for review. Comments due to Isalee by 3/15/12. Isalee to keep current list with all R5 updates. | Cecilia | 2012-02-29 | 2012-03-27 | 2012-04-03
47 | Superfund Greener Clean-up Strategy | Need to create process/schedule for site visits/inspections for implementation of green standards/practices. Will conduct 3-4 inspections this FY after May. Brad Bradley to attend as well. | Durno/Halbur | 2012-03-20 | 2012-03-27 | 2012-04-03
48 | List of OSCs to meet with Mathy | Need to create list of OSCs to meet with Mathy via conference call for an hour each month. Faryan covered Feb at OSC Readiness. Benning to cover March. Need list for rest of FY. All Section Chiefs provided names. Jon to populate calendar with names for rest of the year. | All Chiefs | 2012-03-20 | 2012-04-10 | 2012-04-10
49 | SPCC Refresher/Inspections | Barb Carr working on SPCC refresher webinar and associated field inspections for OSCs who have had training but need to complete inspections. Webinar will be held in May and June, and associated inspections will be scheduled in Chicago, Detroit, and Cleveland as needed. Jon to send Chiefs list of which OSCs need training. Ann W. will provide update at the end of June. | Ann | 2012-02-14 | 2012-05-22 | 2012-05-15
50 | Removal Tracking Database | Carol Ropski putting together User Manual. Application demonstrated by Ropski/Zanter at 1/25/12 retreat. Zanter is adding tools and reports based on specific requests. Will need SOPs for consistency once complete. Working on migrating to Intranet for easier access. Jason to talk to Division about assigning staff member to work on Removal tracking data entry here and in CERCLIS. LaShonda will be trained on Tracker. Chiefs will then coordinate with LaShonda to enter initial site information. | All Section Chiefs | 2011-12-20 | 5/31/2012 to set framework in place | 2012-05-15
51 | Equipment Warehouse Procedures | Work group formed. Meeting in WB on 3/28 to discuss ideas and procedures for maintaining monitoring and respiratory equipment. ER equipment ID'd and on charge. Lam provided recommendations; Maguire to do the same. Need to develop SOPs. Section Chiefs to remind OSCs that there is PPE in the warehouse they can use. Possible ideas include Contractor Support and/or detailed OSC to assist. Will provide final equipment list to managers/chiefs at June retreat. | Mindy | 2012-03-15 | 2012-06-30
52 | 2012 Equipment List | Draft list routed to all OSCs for comment/ideas. Need to cross check list against ERTG recommendations/National Buy lists. List to be completed by end of April for Chiefs to review. Goal to finalize purchase list by end of May. Mitchell to brief Chiefs on process/updates at June 7 ERB retreat in Willowbrook. List finalized on 6/7. Jeff Borseth has been provided list and will begin process of purchasing equipment. | Mike | 2012-02-29 | 2012-06-07 | 2012-06-07
53 | Inland Sensitivity Atlases On-Line availability | Need to ensure Inland Sensitivity Atlases are on-line so that all PDOs and OSCs can access them at any time. Need to be password protected, but may possibly share access with other stakeholders such as USCG. Barbi polling all PDOs to see who needs them. All PDOs have complete set of Atlases on DVDs. Jon coordinated purchase of 9 external hard drives for all PDOs and Chicago EOC/Back-up Responder and these have been distributed. Ann workied with RMD to repair link for access to Atlases for all OSCs. | Ann | 2012-04-17 | 2012-06-07 | 2012-06-07
54 | Core NAR ER/CBRN | Website ready. Review with HQ scheduled for 7/11. Everything posted by team leaders to website by 6/1. Internal review conducted on 6/6. Revisions to work books have been posted. | Charlie | 2012-04-03 | 7/11/12 HQ review | 2012-07-03
55 | New USCG and EPA CBI and Invoicing Procedures for Oil Sites | Have POs follow-up with START and ERRS contractors regarding new agreement with USCG regarding CBI and invoicing for oil sites and ensure contractors are following the new requirements. | Cecilia | 2012-06-26 | 2012-07-20 | 2012-07-10
56 | Google Earth Licenses | HQ will now only provide 5 to ERBs (vs. one for every OSC). SFD also has 10 others. Each license good for 2 computers. Need to prepare list of who has licenses currently, and propose who should receive licenses taking into account limited availability. | Ann/Mike McDonough | 2012-07-03 | 2012-07-31 | 2012-07-10
57 | R5 Flex Viewer | Discussed at 6/7 retreat and moving forward. Brian Cooper working on developing system for Region 5. Platform will include Inland Sensitivity Atlases. START to assist with cost estimate. Purchasing has been initiated on some items. | Mindy/Brian Cooper | 2012-05-23 | 2012-07-31 | 2012-08-01
58 | Removal Support/Homeland Security expenses | Sam routed spreadsheets to all Chiefs. Cecilia and Mindy to take lead. All Chiefs to provide information before 8/21/12 so Jason/Sam can review. Jason and Sam will finalize on 8/22/12 and forward to HQ. | All Chiefs | 2012-08-02 | 2012-08-21 | 2012-08-22
59 | AM/Enforcement documents sign off process | Further work needed in regards to sign-off flowchart and possible electronic documents. One goal is to protect OSC ability to issue verbal orders in the field. All have agreed Notice Letters will be signed in ERBs. Jason/Sam/Wendy reviewed routing slips and forwarded to Sharon. Sharon has agreed to routing slips. Mike will ensure we have current versions, and that Tom Marks is in the loop. ERBs will start to use new forms effective immediately. | Mike | 2011-08-23 | 2012-08-15 | 2012-08-28
60 | FRP update on review status | All OSCs have received at least four plans to review. Nine plans are still outstanding. If they are not reviewed by 8/31/12, the OSCs will be brought back to their offices to finish. New FRPs will be assigned on a rotational basis to all OSCs per a random draw that will start with Joe Fredle and proceed alphabetically. Alex will continue to track review status, and Mindy will provide weekly updates. | Mindy/All Chiefs | 2011-07-11 | Reviews on-going; | 2012-09-04
61 | Complete Form 5170 for 2013 OSC Trainings in Chicago and Angola, IN | Prepare EPA Form 5170 and supporting documentation and route through RA's Office for approval for 2013 R5 OSC trainings in Chicago and Angola, IN. HQ has advised that we proceed with not reporting contractor costs for Angola as they are all technical in nature. Cover Memo modified per RA's question. Forms themselves also revised on 9/11/12. RA approved forms on 9/13/12. Forms submitted to HQ on 9/14/12. Forms will have to be updated and resubmitted with final costs after the events. | Michelle | 2012-06-26 | 2012-09-18 | 2012-09-14
62 | 2013 ER Schedule | FY2013 ER Schedule completed. Indy rotation was added to the schedule. Seniority list was updated and Charlie will route to Jason/Sam for review. Memo drafted for approval of PDO pay. PDO List revised with latest member added. | Charlie/Mark | 2012-05-29 | 2012-09-18 | 2012-09-26
63 | Anthrax Medical Countermeasures Implementation | Work with Glover to roll out R5 anthrax medical countermeasures prescription program procedures consistent with June 14, 2012 memo. Glover has indicated Chicago OSCs will receive prescription when they have annual physical. Chicago OSCs who have already had physicals should make appointment for short meeting with doctor to receive prescription. Need to clarify process for outstationed OSCs. Prescription pads being sent to Akron/St. Louis. Memo sent to all OSCs on 9/25/12. | Mike/Glover | 2012-06-26 | 2012-10-02 | 2012-09-25
64 | Over Time Discussion | Anticipating budget cuts for FY13, including available salary dollars. Division has asked for plan to limit/monitor Overtime. Branch Chiefs reviewed OT usage, and the majority of sites are less than 20 hours per pay period. Section Chiefs to send message to all OSCs with guidelines. No limit on ERs, no OT on PRP oversight jobs, 20 hours limit per pay period for removal actions. | All Chiefs | 2012-09-25 | 2012-10-02 | 2012-10-02
65 | 2012 End of Year Report | Content discussed at Branch Retreat on 8/15/12. Draft submitted to Division and all Chiefs on 9/21/12. Final metrics/report due to Division no later than 10/5/12. Final submitted on 10/4/12. | All/Bev/Michelle | 2012-07-24 | Draft submitted 9/21. Final due 10/5. | 2012-10-04
66 | New OSC Mentoring Meetings; Training Plans | Michelle has met with Andy/Jacob/Betsy/Jason and their mentors. Chart with limited remaining training for all four OSCs has been routed to all Chiefs. Message sent to all four and their mentors encouraging them to continue to work together. Mentoring checklist was revised and routed for review. Comments received and checklist being finalized. | Michelle | 2012-01-01 | 2012-11-20 | 2012-11-27
67 | National/Regional Honor Awards | Nominations are due to Barbi on 11/28. Agreed nominations (and author) are: Eastern Sandusky Team for Gold/Silver medal (Durno); Primary NATO Team (Mitchell/Faryan/Zintak/Ruesch/Cooper/Ursic?) for Collaborative Leadership in Problem Solving (Ribordy); Carl Norman for Financial Stewardship (Cecilia). | All Chiefs | 2012-11-14 | 2012-11-28 | 2012-11-28
68 | Consultation Procedure for Off-Reservation Sites | Chiefs need to provide comments to Jane Neumann on draft white paper. Mark forwarded ERBs comments. Feedback from Jane indicates that nothing will change for OSCs - exemptions granted for Emergencies and Time Sensitive cleanups. | Mark | 2012-11-21 | 2012-11-28 | 2012-11-28
69 | SF Work at Home Exercise | Exercise scheduled for 12/11. Work to be completed before then includes message to all staff, Adobe Connect preparations for Rick's Tuesday meeting. Initial Adobe Connect dry run uncovered serious bandwidth issues when using wireless connections. Steve has notified Rick/Doug that wireless connections (MiFi or other wireless routers) are not the best platform for Adobe Connect and there is no way to improve connection wirelessly. Training for Division continues. ERBs Chief Call will be on via Adobe Connect that week as well. | Bev/Steve | 2012-10-24 | 2012-12-11 | 2012-12-11
70 | RICT Training/COOP Exercise | Scheduled for 12/14 AM in Willowbrook. All Divisions to present on Homeland Security issue - ours will be Bio Watch. Len Zintak will present. He is on Primary response Duty that week. If he is not available, Jaime will present and arrangements will be made to tie Zintak/Durno in on conference call to assist with answering questions. Steve Padovani will make certain COOP Warehouse is organized, and will attend Exercise. | Bev/Mike/Steve | 2012-10-24 | 2012-12-14 | 2012-12-14
71 | IMAAC/NARAC issues | DTRA now in charge of IMAAC. Conflicting information regarding how to access the services, and what constitutes an official activation. Mitchell/ Gulch/Justice have been in discussion with DTRA. They are assisting DTRA in developing SOPs for EPA requests, and they will provide training for OSCs in January. Jim Mitchell briefed all RMs nationwide on call on 11/28. Gulch/Mitchell/Justice will participate in exercise with DTRA to evaluate issues. | Mitchell/Gulch (Charlie/Mindy) | 2012-10-17 | TBD | 2012-12-18
72 | Excellence in ER Award | New award for those with years of service to ER program. Similar to 20 year OSC Award. All agree Geishecker and Micke will be nominated. Michelle clarified with HQ: award for past and current employees; no idea on how many nominees will be received per Region. Geishecker write-up and Micke write-ups submitted. Charlie to represent R5 on awards panel. | Michelle/Bev/ Mike for write-ups; Charlie on review panel | 2012-10-24 | 2012-11-30 | 2012-12-18
73 | Enbridge Spill Mapping | RA has requested mapping of Enbridge pipeline system and associated spill locations and narrative. Padovani led team including Cooper, Clements, Whelan and possibly more. Rick received weekly progress updates. Final priduct delivered to RA. | Padovani/Clements | 2012-12-05 | 2012-12-18 | 2012-12-18
74 | HQ Presentation for OSC Readiness | Regional update presentation will be needed for OSC Readiness. Highlights to include Christenson/Micke retirement, Length of Service awards (Gulch, Justice, Kelly, Kimble - 10 years), Lippert Award, Muller Transfer, 2012 OSC and Peer OSC of the Year. Michelle and Pam developed. Submitted to Peter Oh in HQ on 1/9/13. | Michelle | 2012-11-19 | 2013-01-17 | 2013-01-09
75 | 2013 Response Schedule Vacancies | Request for volunteers routed to all OSCs. Michelle will track volunteers and update schedule. If any vacancies are not filled by 12/31/12, OSCs will be assigned. Ruesch will replace Micke as PDO in new year. Westlake vacancies full; two Back-up weeks still vacant in Chicago. Faryan has agreed to take Back-Up week of 4/5. Charlie will notify Anita via email of her assignment of Back-up week of 3/22. All vacancies filled and updated schedule posted on Quick Place. | All Chiefs | 2012-11-16 | 2013-01-22 | 2013-01-18
76 | Collecting AAA Tokens | All ERB personnel should turn in their AAA tokens, as they are no longer needed/working. Cost associated with outstanding tokens that have not been turned in. Steve to get current list of outstanding AAA Tokens and route to all Chiefs. OSCs will be polled at January training. Steve to follow-up on remaining AAA tokens not turned in. Steve also will remind IMB that tokens should be taken out of service and we should not be paying for the service. | All Chiefs | 2012-12-05 | 2013-01-31 | 2013-01-22
77 | Verizon Navigator | Need to compile list of personnel who don't use/want Verizon Navigator on their Blackberries so we can turn off the service and save the associated fees. OSCs polled at January training. Steve to talk to Ernie and have service turned off for those who were not interested. | All Chiefs | 2012-12-05 | TBD | 2013-01-22
78 | Regional Response Team 2012 End of Year Report | Sam/Jason provided comments. Comments incorporated and report sent to HQ. | Mindy | 2013-01-09 | 2013-01-31 | 2013-01-29
79 | National Notable Achievement Awards | Call for award nominations anticipated soon. All agree on nominations (and author) as follows: OSC - Justice (Durno); Oil - Tzallas (Clements); Homeland Security - Mitchell (Gebien); Superfund Team - Eastern Sandusky (Durno). Rewrites were submitted to Barbi 2/25. Branch Chiefs request copies of all final write-ups. | All Chiefs | 2012-10-24 | 2/20/13 to Barbi Lee; 2/25 for rewrites to Barbi Lee | 3/19/2013
80 | EOC Team | Continue assigning new volunteers to specific positions within EOC. Staffing chart for EOC overall, as well as for 2013 IMT exercise, sent to Branch Chiefs on 2/27. Weekly EOC briefings are on-going. | Bev | 2012-08-15 | 2013-04-01 | 2013-03-26
81 | CI Contract w/Apex | We have $75k of removal money in this contract. Quigley/Ruesch/CIC working on work assignments for Pilsen Neighborhood sites. Expect budget to be $69,000. Remaining $6k canmoved to new option year. Option year will be exercised automatically; however, any new funding requests would be subject to RA approval under current protocols. | Cecilia/Mark | 2012-12-03 | TBD | 2013-04-02
82 | Recognizing Linda/Frank and Bill's contributions to Removal | Michelle working with Pam on new plaques. Voting took place in Angola and the winners were announced. Rick Karl sent message regarding winners to all SF. Michelle sent write-ups to nominated parties for Messenger Award. Will announce nominations in January of each year. | Michelle | 2012-01-25 | 2013-04-30 | 2013-04-09
83 | Renewing OSC Credentials | Credentials expire in May. OSCs/Chiefs missing training can apply for OSC credential only (NOT CERCLA or OPA Inspector). All documentation has been submitted to Donna Howard for entry into TMS. All justification memos were submitted to Division on 4/11/13. Credentials will most likely look like the current ones and reference OSC only - CERCLA and OPA information will be stored elsewhere. | All | 2013-01-22 | Justification Memos turned in on 4/11/13. OECA to review. | 2013-04-23
84 | Status of new SF Laptop Computers | Weekly status updates on SF laptops received, configured, and distributed. Distribution listed submitted on 1/9/13. IMB plans to start distribution in April (hopefully). We will send message out to all recipients prior to distribution with details. 193 computers to be distributed. Distribution was started at end of April. Steve will let Chiefs know of any issues. | Steve | 2012-09-27 | TBD | 2013-04-30
85 | FPN Close-out | On-going tracking of Oil FPNs being closed out in a timely fashion. Working with Isalee Coleman and Cincy Finance. Isalee will maintain/reconcile list for ERBs moving forward. | Mindy/Cecilia | 2013-02-26 | On-going | 2013-04-30
86 | 2013 Equipment Purchases | Equipment Committee will start developing suggested purchase list. Funding availability/timeline TBD. The committee will priority rank equipment on the list. Committee is gathering costs and finalizing list to be shared with Chiefs. List being finalized. Purchases on hold pending budget. | Mike/Steve | 2013-02-26 | 2013-05-15 | 2014-05-22
87 | All Supervisors Meeting | ERB is planning next meeting. Meeting rescheduled for 6/11 at 1pm Central in Lake Superior Room. Charlie will update/issue agenda. Agenda to include budget update (Vince/Doug) and possibly new EJ Tool. Deb Smith available on new date. | Charlie/Steve | 2013-02-13 | 2013-06-11 | 2013-06-11
88 | H&S Form Database Development | Develop database to track OSC submittal of quarterly exposure forms and monthly Scott equipment checks. Al Gebien will manage. Spreadsheet should be sent out monthly to Section Chiefs and Branch Chiefs. Database has been created. First email will go out to OSCs in next week. Section Chiefs will be contacted if OSCs do not provide information. | Steve | 2013-06-26 | TBD | 2013-07-02
89 | Warehouse Management Review | Resolve issues identified from the IG Report. All ERB warehouse spaces were evaluated against IG report. No issues indentified. | Steve | 2013-06-26 | TBD | 2013-07-02
90 | START Monthly Reports | Issue has been identified where OSC noted discrepancies and asked for costs to be disallowed on monthly report. Weston did credit hours questioned by OSC for Allison Transmission Site; however, there is a lag in the credit showing up on the invoice. OSC should continue to deny charges. Sam Chummar sent out SOP/process message to all OSCs. OSCs will notify Gail/Sam of dispute; Gail/Sam will coordinate with START, and notify OSC of resolution and/or credit of disputed charges. | Cecilia | 2013-05-28 | 2013-07-16 | 2013-07-16
91 | Core NAR ER/CBRN 2013 | Michelle coordinated Readiness Assessments #1-6. Final summary report and Evaluation Form Templates routed to HQ, R3, R4. Charlie/Steve to coordinate Assessments #7-9. Willowbrook secure phone/fax tested. Chicago equipment still needs to be checked. Charlie sent email to all Leads for Core NAR ER and CBRN reviews. Jon posted all 2013 materials in Element folders on Quick Place and Charlie informed HQ materials were present. Updated IMT plan posted. HQ review conducted on 7/17 at 9am Central/10am Eastern. | All | 2012-11-19 | Readiness Assessments #7-9 TBD; internal call 6/12; Postings due 6/26; HQ review 7/17 | 2013-07-17
92 | Draft a template for CANUSENT | Received update from EC. HQ wants each RA to sign their own. Rick signed cover memo and forwarded to RA's office. RA signed on 8/9/13. Forwarded to R2. | Mindy/Jason | 2011-01-01 | 2013-08-01 | 2013-08-13
93 | ERBs Removal SOPs/ Strategic Plan | Briefed OSCs on plan at Angola training; Mark sent plan and requested volunteers from staff. Also forwarded to Jaffess/Bouchee to share with their staffs. Discussed path forward during 8/7 ERB Retreat. All agreed on team leads/members for those elements we are going to first focus on. Mark has contacted team leads and they are all on board. Mark will contact all team members to confirm continued interest and explain objectives. Team leads will be asked to conduct a kcik-off meeting. Mark and other Chiefs assigned to teams will provide periodic updates in Chiefs meetings. | Mark/All Chiefs | 2011-03-15 | TBD; next milestone is work group assignments-milestones | 2013-11-13
94 | FRP update on review status | Need to start tracking status of FRP reviews. Some OSCs are falling behind on their review of resubmitted FRPs. Chiefs should remind OSCs to complete reviews asap. Alex routed latest list. All Section Chiefs to provide Branch Chiefs with firm dates for completion of reviews by OSCs in their Sections. All Chiefs provided schedule to Alex. Mindy routed updated list. Alex has started tracking extension dates as well as original due dates. Alex will let Section Chiefs know of any OSCs who have not shown much progress in their reviews. Mindy routed updated list at end of FY13. She will continue to update Chiefs on progress. | Mindy/All Chiefs | 2013-04-23 | On-going | 2013-11-13
95 | FY 2014 Response Schedule | Final schedule was routed to all. Phone Duty Officer eligibility list was updated and will be routed. OSC Lall has announced he will retire at end of December 2013. OSC Augustyn accepted his PDO slot and RS1/2 OSCs volunteered for all of his response weeks. | Mark/Mike/Charlie | 2013-06-26 | 2013-12-31 | 2013-11-13
96 | START TDDs | There are currently 272 open START TDDs, including 46 removal TDDs. 65 TDDs were closed in September. Section Chiefs should advise OSCs to approve monthly invoices for older sites so we can close them out. Cecilia will provide monthly updates on numbers at the end of each month. Cecilia and her section will make arrangements to ensure new contractor is advised of policy for closing out TDDs in a timely fashion. START 4 Goal: All POs/OSCs/Contractors need to be aware of expectation that all TDDs will be closed out within six months of work completion. | Cecilia/Chiefs | 2012-08-15 | On-going | 2013-11-13
97 | FY2013 End Of Year Report | Sam routed draft version to Rick on 9/13. Final 2013 site numbers are expected from HQ on 11/1/13. Final numbers were added to the report and the final version was routed to all Chiefs and the Division. Agreements on how to track EJ sites/dollars were agreed upon in 11/13/13 retreat, and Bev will work with Carol and Jack on changes. | Michelle/Bev | 2013-07-16 | Final version due asap after 10/1. | 2013-11-13
98 | Flexiplace Update | Mark briefed all Removal Managers on discussions with HR regarding flexiplace at 11/13 ERBs Retreat. | Mark | 2013-09-17 | 2013-11-13
99 | Contact for New Oil Workgroup - Dilbit/Bakkan Oil | Designate OSC to represent R5 on new OPM workgroup working on this issue and associated training needs. OSC Dollhopf was selected. | All Chiefs | 2014-01-29 | TBD
100 | PR for Anthrax Prophylaxis | Prepare PR to fill emergency prescriptions. PR prepared - Jason signed it on 2/4/14. | Steve | 2014-01-21 | TBD | 2014-02-04
101 | First Responder Training | Glen Cekus has historically conducted this outreach. He may be retiring this Spring, and has offered to coordinate with replacement. Typically offered 5-10 times per year to Tribes and others. Full day General HazMat/SARA Title III course with START support. This issue was discussed at the 2/19 retreat and follow-up information is available in the minutes for that meeting. | Mike | 2014-01-29 | 2014-02-19 | 2014-02-19
102 | National Notable Achievement Awards | We will submit the following write-ups: Enforcement Team - Lindsey Light (Gebien); Homeland Security - Gene Jablonowski (Padovani); OSC of the Year - Paul Ruesch (Ribordy); Oil - Oil Planners (Clements). | All Chiefs | 2014-01-29 | 2/18 to Barbi | 2014-02-19
103 | Removal Response Weather (Climate Change) Checklist | Need more clarification from OEM before deciding how to implement. OEM provided checklist - we responded with a no. | All Chiefs | 2014-01-23 | TBD | 2014-02-19
104 | Improving Teamwork between CICs/OSCs | We asked Yolanda Bouchee to attend a weekly Chiefs meeting to discuss steps moving forward. Yolanda presented findings at 3/4/14 Chiefs meeting. | Mindy | 2013-12-17 | 2014-02-28 | 2014-03-04
105 | Vehicle Mileage Form | Instructions and new forms were routed to all ERB staff. Staff to prepare and submit annual acknowledgement form. New mileage tracking forms to be used effective immediately. | Steve | 2014-02-19 | 2014-03-04 | 2014-03-04
106 | Oil Invoice Certification Guidance | Prepare written guidance for all OSCs on how to process/certify oil invoices. Mindy routed SOG on March 7, 2014 | Mindy | 2013-08-13 | 2014-03-07 | 2014-03-07
107 | Peer Awards (OSC and Removal Support) | Voting held in Angola. Paul Ruesch selected as Peer OSC of the Year. Michelle Jaster selected as Removal Support Peer of the Year. Michelle drafted message for Rick to send to all SFD. | Michelle/All Chiefs | 2014-01-29 | 2014-03-18 | 2014-03-18
108 | Midyear Review with HQ | Review scheduled for April 10th at 9am Eastern/8am Central. Sam will be out that week. All OSC Section Chiefs should plan on attending. More details on agenda and preparations to follow. We have everything we need together. Section Chiefs are welcome to attend. Will be discussing the A&L table. Got some information on the dates for Joe K., Joe M. and Bill R. Steve O. didn't provide dates for himself. | All Chiefs | 2014-03-04 | 2014-04-10 | 2014-04-10
109 | ERBs Retreat | Next ERBs Retreat will be Wednesday May 7th in Chicago in the Indiana Room on the 12th Floor. Please forward any agenda items to Michelle asap. | All | 2014-04-08 | 2014-05-07 | 2014-05-07
110 | PDO/Response Schedule Changes | Charlie is updating the PDO Eligibility list and will route to all Chiefs once the Branch Chief's comments are incorporated. Michelle updated schedule with personnel replacing Lall and Holz. New schedule routed to all and posted on Quick Place. Mike to ensure approval memos are prepared for switches involving Jaime's weeks while on detail. Michelle will then update schedule. Update will include removal of Indy column as Sewell will be responder for rest of FY while Lam is on detail. | Mike/Michelle | 2014-02-19 | 2014-05-15 | 2014-05-14
111 | Climate Change Plan | Need to review plan and ensure we meet Removal reporting deadlines. May need to work with Region 7 on this. Mark and Betsy met and she agreed to take the lead and ensure we will be prepared to report out on progress as requested. She will inform us if she needs more assistance. | Mark/Betsy/Shelly | 2014-04-23 | TBD | 2014-05-20
112 | Update EOC Plaques | Michelle will work with Pam Gallichio to procure photos and nameplates for EOC/Office Plaques. Peer displays up in Chicago. Retirement plaqu has been updated..Pam to send updated displays to Grosse Ile and Westlake. Bev/Michelle to see if Debbie or Carol have more info on Joe Malek's dates. | Michelle/Bev | 2014-03-18 | 2014-05-31 | 2014-06-04
113 | Equipment Purchase Wish List | Limited Homeland Security dollars may be available to procure some equipment. Equipment list being finalized and PR process has been initiated. | Mike | 2014-03-18 | 2014-05-31 | 2014-06-04
114 | MLB All Star Game | Game will be held in Minneapolis on 7/15. Associated events will be held 7/11-15. No requests for support received. Mark drafted Resource Summary and will submit to HQ EOC/Tito/Eugene Lee/Sherry Fielding. All R5 responders for impacted weeks will be copied as well. | Mark | 2014-07-01 | 2014-07-07 | 2014-07-08
115 | Blackberry Phone Upgrades | Most OSCs/Managers have received new phones. Old Blackberries should be returned to Ernie asap. Len waiting until off Back-Up Response Duty to switch out his phone - Ernie has confirmed his phone is here. Len received his phone. | Steve/Charlie/Mike | 2012-12-18 | 2014-06-10 | 2014-07-29
116 | SCAT Training for Chicago | Class scheduled for July 22-24 in Chicago and will include refresher component. Initial and refresher classes were completed with much success. Mostly RSC members in attendance, along with several OSCs. | Shelly/Ann Michelle/Bev | 2014-03-25 | Class set for July 22-24 | 2014-07-24
117 | MiFi Replacement/Upgrade Issues | Steve, Jeff Borseth, or Al Gebien can get replacement MiFis if someone needs one - process has been clarified. Steve received and activated all of the pool MiFis. | Steve | 2014-02-19 | All ordered. All distributed asap. | 2014-08-05
118 | FOG - SOPs, Equipment, Training | Steve has determined no Removal SOPs need to be added to FOG database. SF equipment not included in FOG effort due to our existing SOPs. SOP template for any new SOPs has been developed and approved for use Region wide. Steve will have to draft directions for SFD on how to use the new SOP template. All Chiefs may be asked in the future to determine what non credentialed field personnel in their Sections require for training. | Steve | 2014-03-04 | Ongoing | 2014-09-04
119 | Removal Sub Accounts | Update definitions for removal account number subcategories. Evaluating use of all the accounts in order to determine if any can be combined/eliminated. Bev updated sub account definitions and prepared memo for distribution. Jason will have Tracy distribute it to all. | Bev | 2013-09-17 | TBD | 2014-09-24
120 | FY 2015 Response Schedule | Draft FY 2015 Response Schedule. PDO and GI/WL sections are completed. Mike routed to all OSCs and changes are due 9/17. Final FY 2015 schedule was issued and posted to Quick Place on 9/24. PDO Stand-by Pay Memo was signed. | Mark/Charlie/Mike | 2014-06-03 | TBD | 2014-09-24
121 | Tribal Mapping Tool | Brian Cooper working on developing tool with Ralph Dollhopf. Brian/Steve need to confirm with Ann/Ralph that all Tribal interests have been addressed, and that the tool is available on the RRT website. Tool was shared with Tribes at Indian River exercise and was well received. Brian Cooper and Ralph Dollhopf will coordinate training for Tribal nations in Region 5 | Steve/Brian Cooper | 2014-08-12 | TBD | 2014-09-24
122 | EOC Cable Bill Payment Issues | All past overdue bills have been paid. Steve to determine if process for regular timely payment schedule has been established so we do not encounter this every six months or so. In FY15, all Regional Comcast bills will be rolled into one 1 PR/account which SFD will be in charge of. Bea will be POC for billing issues. | Steve | 2014-03-25 | TBD based on billing cycle | 2014-09-24
123 | ERB 2014 EOY Report | Draft sent to Rick and Doug on 9/16/14. Report will not be finalized until mid-October after all metrics can be updated. Please submit final metrics to Michelle/Bev asap. | All | 2014-06-26 | Final issued to Divison and all Chiefs 10/8/14. | 2014-10-08
124 | Core NAR ER and CBRN | Readiness Assessment Tabletop was completed successfully on 7/23/14 with OEM/ERT/R3/R4. Internal call held on 9/10. All information is posted on Quick Place. Mike informed Nancy Jones our site is complete. HQ review held on 10/16. Review went well and HQ asked us to share some best practices. | Mike/Charlie | 2014-01-29 | TTX 7/23; Internal review 9/10; HQ review 10/16. | 2014-10-16
125 | ERB Data Management Plan | Update NATO Data Management Plan and ensure it reflects entire ERB data management protocols. Plan discussed during 9/24/14 meeting. Steve incorporating comments and ensure editing is complete. Plan will be considered a working draft. Steve routed to Chiefs on 11/25. Chiefs routed it to their staffs and compiled comments. | Steve/Brian Cooper | 2014-07-08 | TBD | 2015-01-20
126 | Medical Monitoring Clarification | SHEM Managers agree that nationally OSC medical monitoring meets the guidance set forth in the OSC Health and Safety Manual at a minimum. Tier 1 workgroup will prepare documentation for Removal Manager and HQ review. John Glover has indicated that we should complete our Regional guidance, as the Tier 1 workgroup will not be finished with this for some time. Until then, we will follow what is in place for the Region. New work orders will be available for our review at end of October; will then have to be reviewed by doctors. Goal is to present new plan to OSCs in January. | Matt/Sam/John Glover | 2013-09-03 | Presented plan to OSCs during January 2015 training. Chiefs have copies of new orders. | 2015-01-14
127 | Phone Duty Officer Rotation | Anita will be rotating off PDO schedule this year and Jon Gulch will be new PDO effective 3/22/15. Charlie and Jaime working with Dee to prepare 52s for submittal. Charlie is updating eligibility roster and will route to all once change occurs. | Section Chiefs | 2015-01-21 | Paperwork needs to be processed before 3/22. | 2015-02-03
128 | RSC/EOC/IMT/COOP Plan Reviews | All plans need to be reviewed to ensure process for ordering personnel resources both inside and outside the Region is clear. RSC Plan, IMT Plan SF COOP Annex, and Preparedness and Response Plans are completed. Bev routed revised EOC Plan. New HQ Activation procedures are included in EOC Plan, and these procedures will be shared during an upcoming Weekly EOC call. | Bev | 2014-03-25 | TBD | 2015-02-24
129 | Annual Awards | Group discussed nominations and decided on the following: OSC - James Justice (Matt to draft); SFD Team - Milwaukee Die Cast (Matt/Mike to draft); Homeland Security - Mark Durno (Mark to draft); and Oil - Paul Atkociunas (Jaime/Shelly to draft). Alll write-ups edited the week of March 9-13. | All | 2014-11-12 | Write-ups due to Barbi COB 3/5/15 | 2015-03-17
130 | Basic Technical Writing Courses | Dates are March 16-17 in Chicago and March 25-26 in Westlake. Registration is open on trainex. Chiefs should encourage their staff to register asap as class size is limited to 20. Chiefs will discuss number of staff wanting to travel at a later date. | Michelle | 2015-01-21 | 2015-03-26 | 2015-03-17
131 | Annual OSC and Removal Program Peer Awards | OSC Peer Award coordinators are Nightingale and Sewell. Removal Program Peer coordinators are Keating, Kush, Halbur, Faryan and Jaster. Votes held in Angola. OSC Peer nominees were Halbur, Kimble, Maguire, Mitchell and Simon. Halbur was elected as winner. Removal Peer nominees were Cooper, Gallichio and Whelan. Cooper was elected as winner. Rick Karl sent message to all SFD. Michelle to work with Pam to update EOC displays. | Michelle | 2015-01-21 | 2015-03-13 | 2015-03-17
132 | Dell and HP Laptop Computers | Ken Tindall worked out waiver for Enterprise Image until new laptops are assigned. All new computers are in. Only a few new computers remain to be assigned. IMB is cleaning up some HP laptops for use as pool computers. | Steve | 2014-08-05 | 2015-03-13 | 2015-04-08
133 | New Hire Issues | Engage Glover/Colvin to ensure all medical test protocols for new hires are in place at all locations. Engage Colston to ensure drug test protocols for new hires are in place for all locations. | Mindy | 2015-02-11 | TBD - before next three new OSCs are hired. | 2015-04-07
134 | EPA/USCG Jurisdictions Updated in RCP and all Subarea Plans | RRT Planning Subcommittee will lead effort to review all subarea plans and ensure jurisdictional boundaries are well defined. Workgroup has prepared summary of activities. We will be evaluating possibility of consolidating oil workgroups. Suspect Subarea Plans and/or RCP need to be updated. Suspect meetings with USCG will be necessary. | Matt/Ann | 2014-04-23 | 2015-04-30 | 2015-05-28
135 | Communicating jurisdictional boundaries to all OSCs | Workgroup has been formed to work on how best to communicate/update jurisdictional boundaries to OSCs during normal and ER operations. Workgroup members include Atkociunas, Ruesch, Whelan, Fredle, Mendoza and others. Paul is workgroup lead. We will be evaluating possibility of consolidating oil workgroups. | Matt | 2014-07-29 | 2015-04-30 | 2015-05-28
136 | 5th floor Clean-Up | All areas have been sufficiently cleaned up. | Steve/All | 2015-01-21 | TBD | 2015-06-16
137 | iPad Purchase | We have placed an order for 5 iPads through bulk order process. | Steve | 2015-04-28 | TBD | 2015-06-23
138 | Annual Performance Awards | All awards were submitted electronically before 6/23. | All | 2015-03-17 | All write-ups submitted by 6/19/15. | 2015-06-23
139 | Comcast Accounts | We believe all issues have been straightened out as of Jun 16. Will need to wait and see how billing progresses. Daniel Olsson is our new contact for these matters. | Steve | 2014-10-14 | TBD | 2015-07-07
140 | OSC Development Training and Full Scale Exercise Objectives | Mark drafted objectives/expectations for both the on-going OSC Development Training and Full Scale Exercise currently held every March during Angola training. FSE finalized/distributed on 4/7/15. OSC Development Training finalized/routed on 7/7/15. | Mark | 2015-03-03 | 2015-07-01 | 2015-07-07
141 | Core NAR Tabletop Exercise | Core NAR TTX completed on 8/6. Michelle sent R5 OSC Outreach, Exercise, Training table to Nancy Abrams/Rich Canino per their request. Michelle will forward 2016 R5 IMT Exercise dates to HQ once they are set, as the 2016 Core NAR review will center on the IMT exercises nationwide. | All | 2015-03-27 | TTX is 8/6/15 in EOC Conference Room | 2015-08-11
142 | R5 Equipment Team and Equipment Needs | Approved list is final. All PRs are in the system. Jeff Borseth polling OSCs to determine who needs fire resistance coveralls. | Mike | 2015-01-21 | TBD | 2015-08-18
143 | All ERB Engagement | Contracts Section has indicated that they would like to be involved with more activities with OSCs. All ERB employees should be encouraged to participate in Weekly EOC Briefs. CMS/RMs sponsored first event (bagels and coffee) during all ERB meeting on Aug 27. Chiefs - please pay Sam Chummar if you have not already done so. | Matt/Ed | 2015-02-11 | TBD | 2015-09-09
144 | R7 OIG START Audit Follow-up | We need to prepare written report to Rick regarding any R5 issues that were highlighted in findings of R7 OIG START audit. Sam Chummar and Steve Peterson will lead committee, which will also include Jaime and a CO. Sam and Steve continue to develop action items. | Ed/Jaime | 2015-07-28 | TBD
145 | FY 2016 Response Schedule | Mike routed FY 16 Response Schedule to all on 9/21/15. Schedule was also posted to Share Point site. Mike preparing memo for RA. | Mark/Mike | 2015-05-28 | Switches due 9/16. Finalize by 9/22. | 2015-09-21
146 | ATSDR Meeting | Mark Johnson from ATSDR will participate at the beginning of our Chiefs meeting on 9/29. Topics for discussion will include R5 Env Health Specialist hire, ATSDR Director Nov visit, ATSDR support activities feedback, and IL/OH ATSDR gaps/loss of funding. Please send any additional topics and specific feedback to Mindy. | Mindy | 2015-08-18 | 2015-09-29 | 2015-09-29
147 | FY 2015 End of Year Report | Draft submitted to Rick on 9/21/15. Final updated metrics due to Michelle/Bev no later than 10/15. Michelle/Bev will then finalize report. Report was finalized and distributed on 10/16/15. | All | 2015-07-01 | Finalize in mid-October | 2015-10-16
148 | 2015 Honor Awards | Mindy nominated Jason Sewell for Trudy A. Spenicer; Mike nominated the Galena ER for a Gold Medal. | All Chiefs | 2015-09-29 | Write-ups due to Barbi 12/7 noon. | 2015-12-14
149 | PARS/Security Clearance Language | Matt routed list of ERB personnel with current security clearances and required PARS language. All Chiefs need to ensure the language is in their appropriate employees' PARS agreements. | All Chiefs | 2015-11-24 | TBD | 2016-01-19
150 | OSC for Health and Safety Manual Workgroup | Kathy Halbur volunteered to replace Paul on this committee and was approved. Charlie/Mindy will ensure Paul and Kathy meet to transition duties. | Charlie | 2016-02-02 | TBD | 2016-03-15
151 | Enbridge/Kalamazoo River FOSC Report | Rick has indicated we can issue report. Jeff Kimble briefed the RMs on 1/19/16. Jeff will remind ORC we are ready to issue report and ask Ann Rowan if a press release is needed. Report will be issued (in electronic format only) after final change made. Matt will ensure SFD notified before report is posted. Report posted 4/8/16. | Matt | 2013-07-30 | TBD | 2016-04-08
152 | RRT Invitation to Absent Federal Agencies | We have been asked to send invitation letters to Federal agencies that have been absent from RRT meetings for some time. Barbi and Scott Binko are coordinating letters to be sent. Matt signed letters for Jason and forwarded them to USCG to issue in advance of May meeting. | Matt | 2015-11-24 | TBD | 2016-04-12
153 | RRT Downstream Notification Procedures | RRT agreed on language for RCP/ACP regarding prompt alerts and coordination with responders in downstream jurisdictions. Plan revisions and a notification exercise need to completed by 4/7/16. HQ approved CP Brownsville Train Derailment ER as our 2016 notification exercise and we provided requested additional information. | Matt | 2015-10-27 | 2016-04-07 | 2016-04-01
154 | Mid Year Review with HQ | Region 5's mid-year review with HQ is scheduled for April 21 at 9am central. All Section Chiefs invited to participate if interested. Matt/Mick will provide updated numbers to Branch Chiefs next week. | Matt | 2016-04-21 | 2016-04-21 | 2016-04-21
155 | 2015 National Notable Achievement Awards | The following nominations were agreed upon: Shelly Lam - OSC (Mindy to write); Paul Atkociunas - Oil (Charlie/Matt); Galena ER - SFD Team (Mike); Brian Cooper - SFD Person (Steve); Beverly Kush - Homeland Security (Matt). Awards committee has met. Lam, Cooper and Kush write-ups will go forward. Galena will go forward as Oil award. Section Chiefs must assist with award re-writes. | All Chiefs | 2015-12-09 | As set by Barbi Lee and Awards Committee | 2016-04-26
156 | 2016 Core NAR | Core NAR TTX held in Region 4 on 3/21. Mike attended in person; others (including R5 Water Team) participated via adobe connect. IMT Exercise audit, Core NAR checklist and equipment/warehouse audit conducted the week of May 4-6. | Michelle (for coordination); Steve (for warehouse); | 2015-11-24 | 2016-05-06 | 2016-05-06
157 | Secure Room Fax | Fax and phone have been programmed. Test fax completed. | Matt/Sam B. | 2015-10-13 | 2016-05-06 | 2016-05-06
158 | Chicago EOC Plaques | Michelle working with Pam Gallichio and Jeff Borseth to update plaques. All plaques have been updated in Chicago, Grosse Ile and Westlake. | Michelle | 2016-02-02 | 2016-04-30 | 2016-05-31
159 | Supervisor Expectations Memo/Supervisor Site Inspection Checklist | Jason/Sam routed Final Memo. Section Chiefs should ensure that they are using the final version of the checklist which includes questions for meeting with contractors on-site. | All Chiefs | 2016-05-03 | 2016-06-14
160 | Equipment Team/ Equipment Purchase List | Jason/Sam approved FY 2016 list. Mike confirmed Jeff Borseth has completed all associated PRs. | Mike | 2016-04-12 | 2016-07-31 | 2016-10-04
Note on A56: Ribordy, Michael: