## SitRep
TITLE
Region _ Daily Cost Estimates Report-Situation Report
DATE
| Authorized Ceiling | EPA Est.Personnel Cost | EPA Est. Travel Cost | Estimated Contract/Purchase Spent | TOTAL Estimated Expenditures | Balance (Ceiling minus Expenditures) | TOTAL Contract/Purchase OBLIGATIONS. | Est. Daily Burn Rate | Un-Obligated Dollars Remaining | Dollars Obligated Not Spent
MISSION ASSIGNMENT NUMBER 1 | 21343819.9257 | 2144244.23 | 552223.97 | 10714730.02 | 13411198.22 | 7932621.7057 | 16394123.88 | 213668.3774 | 2253227.8457 | 5679393.86
MISSION ASSIGNMENT NUMBER 1
TOTALFUNDED | 21343819.9257 | 2144244.23 | 552223.97 | 10714730.02 | 13411198.22 | 7932621.7057 | 16394123.88 | 213668.3774 | 2253227.8457 | 5679393.86
Region 6 Indirect Rate 13.12% | 2800309.1743 | 281324.843 | 72451.7849 | 1405772.5786 | 1759549.2065 | 1040759.9678 | 2150909.0531 | 28033.2911 | 295623.4934 | 745136.4744
GRAND TOTAL | 24144129.1 | 2425569.073 | 624675.7549 | 12120502.5986 | 15170747.4265 | 8973381.6735 | 18545032.9331 | 241701.6685 | 2548851.3391 | 6424530.3344

## Summary
TITLE
Region_ Daily Cost Estimates Report
DATE
Funding Source | Authorized Ceiling | EPA Est.Payroll Cost | EPA Est. Travel Cost | Estimated Contract/Purchase Spent | TOTAL Estimated Expenditures | Balance | TOTAL Contract/Purchase OBLIGATIONS. | Est. Days Remaining | Est. Daily Burn Rate | Un-Obligated Dollars Remaining | Dollars Obligated Not Spent
USCG PRFA FPN N10036 $24,144,129 Total | 21343819.9257 | 2144244.23 | 552223.97 | 10714730.02 | 13411198.22 | 7932621.7057 | 16394123.88 | â | 213668.3774 | 2253227.8457 | 5679393.86
TOTAL AUTHORIZED FUNDED | 21343819.9257 | 2144244.23 | 552223.97 | 10714730.02 | 13411198.22 | 7932621.7057 | 16394123.88 |  | 213668.3774 | 2253227.8457 | 5679393.86
Region 6 Indirect Rate 13.12% | 2800309.1743 | 281324.843 | 72451.7849 | 1405772.5786 | 1759549.2065 | 1040759.9678 | 2150909.0531 |  | 28033.2911 | 295623.4934 | 745136.4744
Cumulative Total | 24144129.1 | 2425569.073 | 624675.7549 | 12120502.5986 | 15170747.4265 | 8973381.6735 | 18545032.9331 |  | 241701.6685 | 2548851.3391 | 6424530.3344
Estimated Days Remaining
Days remaining based on authorized direct ceiling minus total payroll, travel, and contracts EXPENDED | [7 empty] | 37.1259
Days Remaining based on authorized ceiling minus total payroll, travel, and contract OBLIGATIONS | [7 empty] | 10.5454
Taken from Mission
Assignment or
FPN OPA Funding
Source.
Note: Idirect Rate is
taken out of total
funding.
See Payroll Travel Tab.
FORMULA:
='Payroll Travel'!H8
See Payroll Travel Tab.
FORMULA:
='Payroll Travel'!H18
See Contracts Tab.
FORMULA:
=+Contracts!D44
(Payroll + Travel + Contract Spent)
FORMULA:
=SUM(C7, D7, E7)
(Ceiling minus Expenditures)
FORMULA:
= SUM(B7-F7)
(Taken from Contracts Tab - Total Contract Obligations)
FORMULA: =+Contracts!C44
(Taken from Contracts Tab - Total Contract Obligations)
FORMULA: =Conracts!F44+'Payroll Travel'!C25
FORMULA: =SUM
(B7-H7-C7-D7)
FORMULA: =SUM(H8-E8)
Authorized Ceiling minus Total Expenditures divided by Daily Burn Rate. FORMULA: =SUM(B8-F8/J8)
Authorized Ceiling minus Payroll, Travel, Contracts divided by Daily Burn Rate. FORMULA: =SUM(B8 + H8+C8+D8/J8)

## Contracts
This is an example of a tracking sheet that was previously used. There are many ways to track this data. You should get a daily cost report which also includes the contractors burn rate. So the "Spent" numbers below come from the contractors.
FUNDING METHOD | TITLE/CONTRACT/TASK ORDER | Obligation | Est. Spent | Balance | Daily Burn Rate | Days Remaining
Total EPA |  |  |  | 0 | 0
ERRS T.O. |  | 0 |  | 0 | 0
ERRS T.O. |  |  |  | 0 | 0
| 6MD Equipment Costs (LRVs, generator, satellite kits) | 74000 | 74000 | 0 | 1000
DCN LDR013 | Lab Supplies to process sample CANCELED | 0 |  | 0 | 0
START TDD 0033-10-04-01 | START Location 1 | 4479000 | 2912000 | 1567000 | 50000 | 31.34
START TDD 0033-10-04-02 | START Location 2 | 7391000 | 4455000 | 2936000 | 90000 | 32.6222
START TDD 0033-10-04-03 | START REOC | 1048000 | 680000 | 368000 | 10000 | 36.8
START TDD 0033-10-04-04 | START Location 3 | 494000 | 292000 | 202000 | 6000 | 33.6667
ERT (LDR007,LDR009, LDR044) | TAGA | 888420.1 | 658645 | 229775.1 | 10000 | 22.9775
(LDR008,011,023,025,039,043) | ASPECT | 594000 | 480515.05 | 113484.95 | 6000 | 18.9142
DCN LDR020, LDR046 | Dynamac/DATS ASPECT | 205000 | 130335 | 74665 | 2100 | 35.5548
| START potential IRA (3% of ITD) 6/4-5 | 120990 | 0 | 120990
PRB | Mobil Command Post | 0 | 0 | 0 | 0
Air /cond (LDR003) | HVAC OT/Crescent | 18639.54 | 10466.68 | 8172.86 | 0
GSA (LDR006) | GIS support IA DW47950536 David Parrish PO | 15000 | 0 | 15000
DCN LDR012 | Photo Printer & Supplies | 357.04 | 357.04 | 0 | 0
DCN LDR013 | aquatic biosystems | 120.5 | 120.5 | 0
DCN LDR016 | GSS/Lab Supplies | 16000 | 13144.89 | 2855.11
DCN LDR017 | Hawaiian Marine Imports | 169.08 | 169.08 | 0
DCN LDR019 | Fleet Vehicles | 15333.47 | 7333.47 | 8000
DCN LDR021 | PC/Brescia | 3785.11 | 3783.57 | 0
DCN LDR022 | IDIQ (estimated for 2.5 months per PO) | 35000 | 35000 | 0 | 533
DCN LDR026 | PC/Doherty | 230.48 | 230.48 | 0
DCN LDR027 | PC/Crossland | 109.25 | 109.25 | 0
DCN LDR028 | PC/Katy Miley | 557.84 | 557.84 | 0
DCN LDR029 | UPS Overnight shipping | 70.56 | 70.56 | 0
DCN LDR030 | USGS (GIS) | 15000 | 0 | 15000
DCN LDR031 | aquatic biosystems | 243 | 243 | 0
DCN LDR032 | IDIQ - Ft. Fouchon (estimated for 6 months per PO) | 250000 | 250000 | 0 | 1333
DCN LDR034 | ESAT | 10000 | 10000 | 0
DCN LDR035 | Lab supplies | 382.5 | 382.5 | 0
DCN LDR036 | Supplies (ship samples) | 110 | 59.94 | 50.06
DCN LDR037 | office supplies | 144.06 | 144.06 | 0
DCN LDR038 | IDIQ - New Orleans (estimated for 6 months per PO) | 50000 | 50000 | 0 | 278
DCN LDR040 | Qwilite Biosensor | 16075.44 | 0 | 16075.44
DCN LDR042 | RT Corp/SLA Crude Stand | 100 | 0 | 100
DCN LDR047 | R7 Motorpool | 1045.83 | 0 | 1045.83
DCN LDR048 | PC/Ruhl | 1240.08 | 62.11 | 1177.97
Place Holder | Dioxin Sampling Balloon | 400000 | 400000 | 0
Place Holder | R5 Air Monitor for H2S and team to operate | 250000 | 250000
TOTAL |  | 16394123.88 | 10714730.02 | 5679393.86 | 177244
TAGA charges estimated at $10,000/day, based on contractor info June 4th.
ASPECT charge $6,000/day/flight, $3,000/no fly day).

## Payroll Travel
PAYROLL AND TRAVEL FOR THE XYZ TITLE | Copy Est Cum Total into Previous Cum Total as VALUES
|  | DAILY PAYROLL |  |  | PAYROLL TOTAL COST
PAYROLL: | [5 empty] | NUMBERS ARE ONLY EXAMPLES
|  | Daily Cost |  |  | Estimated Cumulative Total | PAYROLL EXAMPLE | # of Staff | Hourly Cost | # of Paid Hours in shift | Todays Total Daily Cost | Previous Cumulative Total | Estimated Cumulative Total
[6 empty] | MA#01 (CP) | 38 | 65.8 | 11.5 | 28754.6 | 2115489.63 | 2144244.23
|  | 28754.6 |  |  | 2144244.23
HOW TO CALCULATE:
1) Pull Total Payroll Spent (Code 10)from FDW (Reimbursable Agreement Detail Inquiry).
2) Figure out the last pay period end date. Go to FDW-Restricted Access Query-PeoplePlus/CPARS Payroll. |  |  |  | i.e. If the pay period end day is 4/27/10, then choose 4/28/10 to start your days to current date.
3) Calculate how many days from the last pay period end date to current date. |  |  | (74 days 4/28/10 - 7/10/2010)
4) Figure out how long the days are, how many people and the overestimated pay rate, GS 13 Step 9 for example. See Payroll Example Chart. Note: You can also find the number of staff from the IAP From 204 which shows the number of people assigned to the job.
|  | TRAVEL DAILY COST |  |  | TRAVEL TOTAL COST
TRAVEL:
|  | 7669.7774 |  |  | 552223.97 | TRAVEL EXAMPLE | # of Staff | Daily Cost | Todays Total Cost | Previous Cumulative Total | Estimated Cumulative Total
Total Travel est. cumulative FDW total divided by (74 days 4/28/10 - 7/10/2010) = est. daily cost | [5 empty] | MA#01 (CM) | 38 | 202 | 7676 | 26246 | 33922
1) Pull Total Travel Spent (Code 21) from FDW (Reimbursable Agreement Detail Inquiry)
2) Calculate how many days, how many people, and the ME&I Travel Rate for that location.
TOTAL estimated daily rate for salary and travel |  | 36424.3774 |  |  | 2696468.2
Total Payroll Spent($1,942,962.03)+ Todays Daily Cost ($28,755) multiplied by number of days past the last paid pay period end date (7 Days)
$65.80 Estimated EPA hourly cost per employee including salary and EPA share of benefits.
11.5 paid hours for a 7AM -7PM schedule
38 employees
38 employees times $202 estimated costs for per diem, hotel, rental car, etc.
FORMULA:???

## OPA PRFA
[5 empty] | Authorized |  | Estimated |  | Daily Burn
|  |  |  | Dates | Amount | Budget | Spent | Balance | Rate
OPA FPN N10036 |  |  | 06LXDWH | 2010-04-28 | 1000000
|  |  | 06LXDWH | 2010-05-05 | 4000000
|  |  | 06LXDWH | 2010-05-17 | 178429
|  |  | 06LXDWH | 2010-05-29 | 2000000
|  |  | 06LXDWH | 2010-06-05 | 3524700
|  |  | 06LXDWH | 2010-06-10 | 5250000
|  |  | 06LXDWH | 2010-06-30 | 8191000
[5 empty] | 24144129 | 21343819.9257 | 13411198.22 | 7932621.7057 | 213668.3774
Indirect Rate Calculation
Method 1:
- when IAG negotiated without indirect costs (a part of)
| Insert |  | Insert
Direct Cost | Indirect Rate | Indirect Cost | Total
21343819.9257 | 0.1312 | 2800309.1743 | 24144129.1
Method 2:
- when IA negotiated with indirect costs (on top of)
| Insert |  | Insert
Direct Cost | Indirect Rate | Indirect Cost | Total
0 | 0 | 0 | 0

## Contracts reconciliation
DCN | FDW Commit | Sitrep | Description | Obligations
RE 1006LDR001 | 600000
RE 1006LDR004 | 900000
RE 1006LDR005 | 1250000
RE 1006LDR008 | 150000
RE 1006LDR010 | 240000
RE 1006LDR011 | 75000
RE 1006LDR014 | 160000
RE 1006LDR015 | 1100000
RE 1006LDR022 | 35000
RE 1006LDR023 | 85000
RE 1006LDR024 | 1764000
RE 1006LDR025 | 54000
RE 1006LDR032 | 250000
RE 1006LDR033 | 2716000
RE 1006LDR034 | 10000
RE 1006LDR038 | 50000
RE 1006LDR039 | 50000
RE 1006LDR040 | 16075.44
RE 1006LDR041 | 350000
RE 1006LDR043 | 180000
RE 1006LDR044 | 310000
RE 1006LDR045 | 4836000
RE 1006LDR046 | 100000
RQ 1006LDR003 | 18639.54
RQ 1006LDR006 | 15000
RQ 1006LDR007 | 400000
RQ 1006LDR009 | 178420.1
RQ 1006LDR012 | 357.04
RQ 1006LDR013 | 120.5
RQ 1006LDR016 | 16000
RQ 1006LDR017 | 169.08
RQ 1006LDR019 | 15333.47
RQ 1006LDR020 | 105000
RQ 1006LDR021 | 3785.11
RQ 1006LDR026 | 230.48
RQ 1006LDR027 | 109.25
RQ 1006LDR028 | 557.84
RQ 1006LDR029 | 70.56
RQ 1006LDR030 | 15000
RQ 1006LDR031 | 243
RQ 1006LDR035 | 382.5
RQ 1006LDR036 | 110
RQ 1006LDR037 | 144.06
RQ 1006LDR042 | 100
RQ 1006LDR047 | 1045.83
RQ 1006LDR048 | 1240.08
RQ 1007W10132 | 12862.36
Dioxin Sampling Balloon | 400000
R5 Air Monitor for H2S and team to operate | 250000
FDW Total Commitments | 16715996.24
Sitrep Total Obligations | 16394123.88
Sitrep understated (or if negative overstated) | 321872.36
START FDW | 13916000
START PO | 13412000
START Difference | 504000